COMPLETE EXECUTION PLAN

React (Next.js) Directory & Review Platform

From Figma Design to Production Deployment

AI/SaaS/Startup Directory + Inshorts-Style News Engine

11 Phases  |  19 Weeks  |  48 Pages  |  200+ Action Items

Figma Design System  •  Tech Stack  •  Database Schema  •  API Architecture

Frontend (React/Next.js)  •  Backend  •  News AI Pipeline  •  Testing

SEO  •  Deployment (CI/CD)  •  Launch Strategy  •  Team & Budget

March 2026  |  Confidential

# Complete React Execution Plan

AI / SaaS / Startup Directory & Review Platform with Inshorts-Style News

This document provides an end-to-end, step-by-step execution plan covering every phase of building the directory platform in React — from Figma design files through to production deployment, CI/CD pipelines, monitoring, and post-launch iteration. Every task includes the tools, file structures, commands, team roles, and time estimates needed for execution.

## Master Timeline Overview

| Phase | Duration | Weeks | Key Deliverables |
| --- | --- | --- | --- |
| Phase 1: Design System & Figma | 4 weeks | W1–W4 | Complete Figma design system, all page designs, component library, prototypes |
| Phase 2: Project Setup & Architecture | 2 weeks | W5–W6 | Monorepo, CI/CD, DB schema, API contracts, auth scaffolding |
| Phase 3: Core Backend Development | 6 weeks | W7–W12 | APIs, database, auth, admin panel, payment, email system |
| Phase 4: Frontend Development | 8 weeks | W7–W14 | All React pages, components, state management, i18n (parallel with backend) |
| Phase 5: News Engine & AI Pipeline | 4 weeks | W11–W14 | RSS ingestion, AI summarization, categorization, multilingual news |
| Phase 6: Integration & Testing | 3 weeks | W15–W17 | E2E tests, performance optimization, security audit, accessibility |
| Phase 7: SEO & Content Seeding | 3 weeks | W15–W17 | 500+ listings, meta tags, schema markup, sitemap, programmatic pages |
| Phase 8: Launch & Post-Launch | 2 weeks | W18–W19 | Staged rollout, monitoring, bug fixes, first marketing push |

Total timeline: ~19 weeks (4.5 months) with frontend and backend development running in parallel from Week 7 onwards. This assumes a team of 3–5 developers, 1 designer, and 1 content/marketing person.

# Phase 1: Figma Design System & UI/UX Design

This is the most critical pre-development phase. A thorough Figma design system eliminates 60–70% of development ambiguity and prevents expensive redesigns later. Allocate a full 4 weeks here.

## 1.1 Figma Project Structure (Week 1)

Create the following Figma file structure in your team workspace:

- File 1 — Design System: Contains all tokens, components, and patterns. This is your single source of truth.

- File 2 — Pages (Desktop): All page-level designs at 1440px and 1280px widths.

- File 3 — Pages (Mobile): All page-level designs at 375px (iPhone) and 390px widths.

- File 4 — Pages (Tablet): Key pages at 768px and 1024px widths.

- File 5 — Prototypes: Interactive flows for user testing (listing submission, review flow, news browsing).

- File 6 — Admin Dashboard: Separate file for the admin/CMS interface.

- File 7 — Email Templates: Transactional emails (welcome, review request, lead notification, payment receipt).

## 1.2 Design Tokens & Variables (Week 1)

### Color System

- Primary: Deep blue (#0F4C75) — used for headers, CTAs, navigation

- Secondary: Medium blue (#1B6CA8) — used for links, secondary buttons, accents

- Accent: Coral red (#E74C3C) — used for alerts, badges, urgent CTAs

- Success: Green (#27AE60) — reviews, positive indicators, verified badges

- Warning: Orange (#E67E22) — pending states, caution notices

- Neutral 50–900: Gray scale from #FAFAFA to #1A1A2E for backgrounds, text, borders

- Surface: White (#FFFFFF) for cards, Light (#F8FAFC) for page backgrounds

- Dark Mode Variants: Define every color's dark mode equivalent using Figma variable modes

### Typography Scale

- Font Family: Inter (primary), JetBrains Mono (code), Noto Sans (multilingual fallback)

- Display: 48px/56px line-height, -0.02em tracking, Bold — hero headlines only

- H1: 36px/44px, -0.01em, Bold — page titles

- H2: 28px/36px, -0.01em, Semibold — section headers

- H3: 22px/30px, Normal tracking, Semibold — subsection headers

- H4: 18px/26px, Medium — card titles, sidebar headers

- Body Large: 16px/24px, Regular — primary content text

- Body: 14px/22px, Regular — secondary content, descriptions

- Caption: 12px/18px, Regular — metadata, timestamps, labels

- Overline: 11px/16px, Semibold, uppercase, 0.08em tracking — category labels

### Spacing & Layout

- Base Unit: 4px. All spacing derived from multiples: 4, 8, 12, 16, 20, 24, 32, 40, 48, 56, 64, 80, 96, 128px

- Grid: 12-column grid, 1280px max container, 24px gutters (desktop), 16px gutters (mobile)

- Border Radius: sm=4px, md=8px, lg=12px, xl=16px, full=9999px

- Shadows: sm (cards), md (dropdowns), lg (modals), xl (sticky nav)

- Breakpoints: sm=640px, md=768px, lg=1024px, xl=1280px, 2xl=1536px (matches Tailwind)

## 1.3 Figma Component Library (Week 1–2)

### Atoms (Smallest Building Blocks)

- Button: Primary, Secondary, Ghost, Danger, Link × sm/md/lg × default/hover/active/disabled/loading

- Input: Text, Email, Password, Search, Textarea × default/focus/error/disabled + label + helper text

- Select/Dropdown: Single, Multi-select, with search, with tags

- Checkbox, Radio, Toggle: default/checked/indeterminate/disabled

- Badge: Category, Status, Rating, Count × color variants

- Avatar: Image, Initials, Company logo × xs/sm/md/lg/xl

- Star Rating: 0–5 stars, interactive and display-only variants

- Tag/Chip: Category tags, filter tags, removable, clickable

- Icon Set: 80+ icons covering navigation, categories, actions, social (use Phosphor or Lucide)

- Tooltip, Popover, Toast notification variants

### Molecules (Combined Atoms)

- Search Bar: icon + input + filter button + category dropdown + recent searches

- Listing Card: logo + name + category badge + rating + review count + price tag + dofollow indicator + CTA button

- News Card (Inshorts-style): image/gradient + headline + 60-word summary + source + timestamp + category tag + share buttons

- Review Card: avatar + name + rating stars + date + review text + helpful/not helpful buttons + company response

- Comparison Row: tool A logo/name/rating vs tool B logo/name/rating per feature

- Pricing Tier Card: tier name + price + feature list + CTA button + popular badge

- Filter Panel: category checkboxes + rating slider + price range + deployment type + language + clear all

- Breadcrumb: home > category > subcategory > listing name

- Pagination: prev/next + page numbers + items per page selector

- Lead Capture Form: name + email + company + message + schedule demo button

### Organisms (Page Sections)

- Navigation Bar: logo + search + category mega-menu + language selector + auth buttons + mobile hamburger

- Hero Section: headline + subtitle + search bar + category quick links + animated stats counter

- Category Grid: 3–4 column grid of category cards with icon, name, listing count

- Featured Listings Carousel: horizontally scrollable listing cards with featured badge

- News Feed Section: vertical scrollable news cards with category tabs at top

- Review Section: overall rating summary + review distribution chart + individual review cards + write review CTA

- Comparison Table: feature-by-feature comparison grid with checkmarks and values

- Footer: 4-column links + newsletter signup + language selector + social links + legal links

- Sidebar: filters panel + sponsored listing + trending categories + recent news

- Dashboard Shell: sidebar nav + top bar + content area + notification center

## 1.4 Complete Page Designs (Week 2–3)

### Public-Facing Pages (26 pages)

- Homepage: Hero + search + featured listings + top categories grid + latest news + trending tools + stats bar + testimonials + CTA section

- Category Page: Category header + filter sidebar + listing grid (list/grid toggle) + sort dropdown + pagination + related categories + category news feed

- Subcategory Page: Similar to category but scoped. E.g., /ai-tools/chatbots

- Listing Detail Page: Company header (logo, name, rating, CTA) + tabbed content (Overview, Features, Pricing, Reviews, Alternatives, News) + sidebar (quick stats, contact form, similar tools)

- Comparison Page: /compare/tool-a-vs-tool-b — side-by-side feature comparison + pricing + reviews summary + recommendation

- Alternatives Page: /alternatives/tool-name — grid of alternative tools with comparison highlights

- Review Detail Page: Full review with company response + helpful voting + related reviews

- Write Review Page: Multi-step form: select product > rate features > write pros/cons > overall rating > submit

- News Feed Page: Full-screen Inshorts-style news with category tabs + swipe navigation (mobile) + card grid (desktop)

- News Article Page: 60-100 word summary + source link + related listings + share buttons + category breadcrumb

- Search Results Page: Query + results grid + filters + did-you-mean + related categories

- Pricing Page: 3–4 tier cards + feature comparison matrix + FAQ + testimonials + CTA

- About Page: Mission + team + stats + press mentions + contact

- Blog/Resources Page: Article grid + category filter + featured article + newsletter signup

- Blog Article Page: Full article layout + author bio + related articles + CTA

- Contact Page: Contact form + email + social links + FAQ section

- Sign Up Page: Email/social auth + company info step + plan selection

- Sign In Page: Email/password + social login + forgot password + magic link option

- Forgot Password / Reset Password Pages

- Submit Listing Page: Multi-step submission wizard (see below)

- User Profile Page: Reviews written + listings claimed + saved tools + activity feed

- "Best Of" Guide Template: Editorial page layout for SEO content

- Annual Report/Award Page: Dynamic report page with category winners

- Legal Pages: Privacy Policy, Terms of Service, Cookie Policy (3 pages)

- 404 and Error Pages

### Dashboard Pages — Listed Company (12 pages)

- Dashboard Home: Overview stats (views, clicks, leads, reviews this month) + quick actions + alerts

- Profile Editor: Edit company details, logo, screenshots, videos, pricing, integrations, team

- Analytics Page: Charts for views, clicks, leads over time + geographic breakdown + keyword rankings + competitor benchmarking

- Reviews Management: All reviews + respond to reviews + review request campaigns + review widgets/embeds

- Leads Page: Lead list + lead detail + export + CRM integration settings

- Buyer Intent Page: Who viewed your profile + company/persona data + intent score (Pro/Enterprise)

- Comparison Pages Manager: See all comparisons involving your tool + request corrections

- News Mentions: All news articles that mention or relate to your category

- Badges & Awards: Earned badges + eligibility tracker + embed code generator

- Billing Page: Current plan + upgrade/downgrade + invoices + payment methods

- Settings: Team members + API keys + notification preferences + integrations

- Support/Help: Knowledge base + ticket submission + live chat

### Admin Dashboard Pages (10 pages)

- Admin Home: Platform-wide KPIs (total listings, reviews, revenue, traffic, signups today)

- Listing Moderation Queue: Pending listings + approve/reject + edit before publish

- Review Moderation Queue: Flagged/reported reviews + approve/reject + fraud detection

- News Management: AI-generated news queue + edit summaries + approve/reject + schedule

- User Management: User list + roles + ban/suspend + impersonate

- Category/Taxonomy Manager: Add/edit/merge categories + set hierarchy + manage slugs

- Revenue Dashboard: MRR, ARR, churn, upgrades, payment failures, refunds

- SEO Dashboard: Top ranking pages + broken links + missing meta + sitemap health

- Content Manager: Blog posts + guides + email templates

- System Settings: Feature flags + rate limits + API keys + third-party integrations

## 1.5 Interactive Prototypes & User Flows (Week 3–4)

Build clickable Figma prototypes for these critical user journeys:

- Listing Submission Flow (7 steps): Sign up/login → Enter company URL → Auto-populate fields from website → Upload logo & screenshots → Select categories & tags → Add pricing & features → Choose plan & pay → Confirmation + profile preview

- Review Writing Flow (5 steps): Find product → Click "Write Review" → Verify identity (email/LinkedIn) → Rate categories (ease of use, features, support, value) → Write pros/cons/summary → Submit → Confirmation

- Buyer Discovery Flow: Homepage → Search or browse category → Apply filters → View listing → Read reviews → Compare tools → Submit lead/request demo

- News Browsing Flow: Homepage news section or /news → Swipe through cards (mobile) or scroll grid (desktop) → Tap for full summary → Click to source → Share on social

- Dashboard Onboarding: First login → Welcome tour → Complete profile checklist → Request first review → View initial analytics

- Upgrade Flow: Free user → See upgrade prompt in dashboard → View pricing comparison → Select plan → Enter payment → Instant feature unlock

## 1.6 Design-to-Development Handoff Checklist

- All components use auto-layout with proper padding and gap values

- Every interactive element has all states designed (default, hover, active, focus, disabled, loading, error)

- Responsive variants created for desktop (1280px+), tablet (768px), and mobile (375px)

- Figma Variables mapped to CSS custom properties / Tailwind config values

- Component naming matches React component naming convention (PascalCase)

- Spacing annotations on complex layouts (use Figma's measurement tools)

- Motion/animation specs documented: what animates, duration, easing, trigger

- Dark mode variants for all pages and components

- Accessibility: color contrast ratios (4.5:1 minimum), focus states, screen reader annotations

- Export assets: SVG icons, optimized images, any custom illustrations

- Dev mode enabled in Figma for CSS/code inspection

# Phase 2: Project Setup & Architecture

Before writing any feature code, establish the entire project foundation. This takes 2 focused weeks and saves months of technical debt.

## 2.1 Final Tech Stack Decision

| Layer | Technology | Why This Choice |
| --- | --- | --- |
| Framework | Next.js 15 (App Router) | SSR/SSG for SEO, React Server Components, API routes, built-in i18n, image optimization |
| Language | TypeScript (strict mode) | Type safety across full stack, better IDE support, fewer runtime bugs |
| Styling | Tailwind CSS 4 + shadcn/ui | Matches Figma tokens, utility-first, tree-shakeable, shadcn gives accessible base components |
| State Management | Zustand + TanStack Query v5 | Zustand for client state, TanStack Query for server state/caching |
| Forms | React Hook Form + Zod | Performant forms, schema-based validation shared with API |
| Database | PostgreSQL 16 + Prisma ORM | Relational data (listings, reviews, users), full-text search, JSON support |
| Search | Meilisearch (or Typesense) | Instant search with typo tolerance, faceted filtering, multilingual |
| Cache | Redis (Upstash) | Session storage, rate limiting, caching hot queries, job queues |
| Auth | NextAuth.js v5 (Auth.js) | OAuth providers, magic links, JWT sessions, role-based access |
| Payments | Stripe (Billing + Checkout) | Subscription management, invoicing, global payment methods, webhooks |
| File Storage | Cloudflare R2 or AWS S3 | Logo/screenshot/media uploads, CDN-backed delivery |
| Email | Resend + React Email | Transactional emails with React-based templates |
| AI/LLM | OpenAI GPT-4o-mini or Claude Haiku | News summarization, category classification, content generation |
| News Pipeline | BullMQ + Redis | Job queue for RSS processing, AI summarization, scheduling |
| CMS (Admin) | Custom React admin or Payload CMS | Full control over moderation workflows and content |
| Analytics | PostHog or Plausible | Privacy-friendly, self-hostable, funnel analysis, feature flags |
| Monitoring | Sentry + Better Stack | Error tracking, uptime monitoring, log aggregation |
| Deployment | Vercel (frontend) + Railway/Render (backend) | Edge deployment, preview deploys, easy scaling |
| CI/CD | GitHub Actions | Automated testing, linting, deployment pipelines |
| CDN | Cloudflare | Global edge caching, DDoS protection, image optimization |

## 2.2 Monorepo File Structure

Use a monorepo with Turborepo for shared code between frontend, admin, and any microservices:

directory-platform/

- ├─ apps/

- │   ├─ web/                    → Next.js public-facing site + company dashboard

- │   ├─ admin/                  → Next.js admin dashboard (separate deploy)

- │   └─ news-worker/            → Node.js background worker for news pipeline

- ├─ packages/

- │   ├─ ui/                     → Shared React component library (maps to Figma)

- │   ├─ database/               → Prisma schema + migrations + seed scripts

- │   ├─ shared/                 → Shared types, Zod schemas, constants, utils

- │   ├─ email/                  → React Email templates

- │   └─ config/                 → ESLint, TypeScript, Tailwind shared configs

- ├─ scripts/                        → Seed data, migration helpers, deployment scripts

- ├─ docker/                         → Docker Compose for local development

- ├─ .github/workflows/              → CI/CD pipelines

- ├─ turbo.json                      → Turborepo pipeline config

- ├─ package.json                    → Root workspace config

- └─ .env.example                    → Environment variable template

## 2.3 Database Schema Design (Core Tables)

Below are the primary database entities. Each has created_at, updated_at, and soft-delete (deleted_at) fields.

| Table | Key Fields | Relationships |
| --- | --- | --- |
| users | id, email, name, avatar_url, role (user/company/admin), locale, email_verified_at, password_hash | has_many: reviews, listings (as owner), sessions |
| companies | id, user_id (owner), name, slug, logo_url, website, description, founded_year, team_size, funding_stage, hq_country, status (draft/pending/active/suspended) | belongs_to: user; has_many: listings, reviews (received) |
| listings | id, company_id, name, slug, tagline, description_json (rich text), category_id, subcategory_ids[], pricing_model, price_from, demo_url, screenshots[], video_url, features_json, integrations[], plan_tier, dofollow_enabled, featured, verified | belongs_to: company, category; has_many: reviews, comparison_entries |
| categories | id, name, slug, description, icon, parent_id (self-referencing for hierarchy), listing_count, sort_order | has_many: listings, subcategories (self), news_articles |
| reviews | id, listing_id, user_id, overall_rating (1-5), ease_of_use, features, support, value_for_money, title, pros, cons, body, verified, helpful_count, status | belongs_to: listing, user; has_many: review_responses |
| review_responses | id, review_id, company_id, body, created_at | belongs_to: review, company |
| news_articles | id, title, summary (60-100 words), source_url, source_name, image_url, category_id, language, published_at, ai_generated, editor_approved, tags[] | belongs_to: category |
| comparisons | id, listing_a_id, listing_b_id, slug, feature_data_json, auto_generated, views_count | belongs_to: listing (twice) |
| leads | id, listing_id, name, email, company, message, source_page, utm_params_json, status (new/contacted/converted) | belongs_to: listing |
| subscriptions | id, company_id, stripe_subscription_id, plan (free/growth/pro/enterprise), status, current_period_start, current_period_end | belongs_to: company |
| page_views | id, listing_id, visitor_fingerprint, country, referrer, page, created_at | belongs_to: listing (for analytics) |
| badges | id, listing_id, type (top_rated/trending/editors_choice), quarter, year, category_id | belongs_to: listing, category |

## 2.4 API Routes Architecture

Using Next.js App Router API routes (app/api/) for the primary app, with tRPC or REST conventions:

### Public API Endpoints

- GET  /api/listings — List/search listings with filters, pagination, sorting

- GET  /api/listings/[slug] — Single listing detail with reviews summary

- GET  /api/categories — Category tree with listing counts

- GET  /api/categories/[slug] — Category detail + listings

- GET  /api/reviews?listing_id=X — Reviews for a listing, paginated

- POST /api/reviews — Submit a review (authenticated)

- GET  /api/compare/[slugA]-vs-[slugB] — Comparison data

- GET  /api/alternatives/[slug] — Alternatives for a tool

- GET  /api/news — News feed with category filter and pagination

- GET  /api/news/[id] — Single news article

- GET  /api/search?q=query — Full-text search across listings and news

- POST /api/leads — Submit a lead/demo request

### Authenticated (Company Dashboard) Endpoints

- GET/PUT  /api/dashboard/profile — View/edit company profile

- GET      /api/dashboard/analytics — Views, clicks, leads data

- GET      /api/dashboard/reviews — Reviews received + respond

- POST     /api/dashboard/reviews/[id]/respond — Respond to review

- GET      /api/dashboard/leads — All leads with filtering

- GET      /api/dashboard/intent — Buyer intent signals (Pro/Enterprise)

- GET/POST /api/dashboard/billing — Subscription management via Stripe

- POST     /api/dashboard/listings — Submit new listing

- PUT      /api/dashboard/listings/[id] — Edit listing

### Admin Endpoints

- GET/PUT /api/admin/listings — Moderate listings (approve/reject/edit)

- GET/PUT /api/admin/reviews — Moderate reviews

- GET/PUT /api/admin/news — Manage news articles

- GET/PUT /api/admin/users — User management

- GET/PUT /api/admin/categories — Taxonomy management

- GET     /api/admin/analytics — Platform-wide metrics

### Webhook Endpoints

- POST /api/webhooks/stripe — Payment events (subscription created/cancelled/failed)

- POST /api/webhooks/review-verify — Email verification callbacks

## 2.5 Authentication & Authorization Matrix

| Role | Can Do | Cannot Do |
| --- | --- | --- |
| Visitor (unauthenticated) | Browse listings, read reviews, read news, search, view comparisons, submit lead forms | Write reviews, submit listings, access any dashboard |
| User (authenticated) | Everything Visitor + write reviews, save/bookmark tools, claim a company, upvote reviews | Access company dashboard, moderate content, admin functions |
| Company Owner | Everything User + full company dashboard (profile, analytics, reviews, leads, billing, settings) | Moderate other companies, admin functions, edit other listings |
| Company Team Member | Scoped company dashboard access (configurable per-member permissions) | Billing management, delete company, admin functions |
| Admin | Full platform access: moderate all content, manage users, manage categories, view revenue, system settings | N/A (full access) |
| Super Admin | Everything Admin + manage admin users, feature flags, database operations, system configuration | N/A (full access) |

## 2.6 Local Development Environment Setup

Every developer should be able to run the full stack locally in under 10 minutes:

- Step 1 — Clone & Install: git clone repo → pnpm install (using pnpm workspaces)

- Step 2 — Start Infrastructure: docker compose up -d (PostgreSQL, Redis, Meilisearch, MinIO for S3-compatible storage)

- Step 3 — Database: pnpm db:migrate → pnpm db:seed (creates test categories, listings, reviews, users)

- Step 4 — Environment Variables: cp .env.example .env.local (pre-configured for local services)

- Step 5 — Start Dev Servers: pnpm dev (starts web app at localhost:3000, admin at localhost:3001, news worker)

- Step 6 — Verify: Visit localhost:3000 — should see seeded homepage with listings and news

# Phase 3: Frontend Development in React (Next.js)

This phase runs for 8 weeks (W7–W14), parallel with backend development. Organize work by page groups, building shared components first.

## 3.1 Component Development Order (Week 7–8)

Build the shared UI component library first, testing each component in Storybook. This maps directly to your Figma component library:

- Week 7, Days 1–2: Project scaffolding. Set up Next.js app with TypeScript, Tailwind, shadcn/ui initialization, Storybook, testing framework (Vitest + React Testing Library), Playwright for E2E.

- Week 7, Days 3–5: Atoms. Build all buttons, inputs, badges, avatars, rating stars, tags, tooltips, toast notifications. Each gets a Storybook story and unit test.

- Week 8, Days 1–2: Molecules. Build search bar, listing card, news card, review card, comparison row, pricing card, filter panel, breadcrumb, pagination.

- Week 8, Days 3–5: Organisms. Build navbar (with mega-menu), hero section, category grid, featured carousel, news feed section, review section, footer, sidebar, dashboard shell.

## 3.2 Page Implementation Schedule (Week 9–14)

| Week | Pages to Build | Key Technical Details | Developer |
| --- | --- | --- | --- |
| W9 | Homepage, Category Page, Subcategory Page | SSG with ISR (revalidate every 60s), dynamic meta tags, structured data (Organization, ItemList schema) | Dev 1 |
| W9 | Sign Up, Sign In, Forgot Password, Reset Password | NextAuth.js integration, OAuth flows (Google, GitHub, LinkedIn), magic link, form validation with Zod | Dev 2 |
| W10 | Listing Detail Page (all 6 tabs) | Dynamic SSR, tab routing with URL params, lazy-loaded review section, structured data (Product, AggregateRating, FAQ schema) | Dev 1 |
| W10 | Search Results Page, 404/Error Pages | Meilisearch integration, debounced search, faceted filters, URL-synced filter state | Dev 2 |
| W11 | Comparison Page, Alternatives Page | Auto-generated from DB, canonical URLs, SEO-optimized headings, share functionality | Dev 1 |
| W11 | News Feed Page, News Article Page | Infinite scroll (mobile) or paginated grid (desktop), swipe gestures on mobile, social share APIs | Dev 2 |
| W12 | Pricing Page, About Page, Contact Page | Stripe pricing table embed or custom, contact form with Turnstile captcha, team section | Dev 2 |
| W12 | Submit Listing Wizard (multi-step form) | 7-step wizard with progress indicator, auto-save drafts, image upload with crop, URL auto-populate | Dev 1 |
| W13 | Company Dashboard: Home, Profile Editor, Analytics | Protected routes, role-based rendering, Recharts for analytics charts, real-time data via TanStack Query | Dev 1 |
| W13 | Company Dashboard: Reviews, Leads, Billing | Stripe Customer Portal integration, review response form, lead export CSV, email notifications | Dev 2 |
| W14 | Company Dashboard: Intent, Badges, Settings | Intent data visualization, badge embed code generator, team member invite flow, API key management | Dev 1 |
| W14 | Admin Dashboard (all 10 pages) | Separate Next.js app, data tables with sorting/filtering (TanStack Table), bulk actions, moderation workflows | Dev 2 |

## 3.3 State Management Architecture

Divide state management into clear domains:

- Server State (TanStack Query): All data fetched from APIs — listings, reviews, news, analytics. TanStack Query handles caching, background refetching, pagination, optimistic updates, and stale-while-revalidate patterns.

- URL State (nuqs or Next.js searchParams): Filters, sort order, pagination, search queries, active tabs. URL is the source of truth so users can share/bookmark filtered views.

- Client State (Zustand): UI state that doesn't belong in URL: sidebar open/closed, modal state, toast queue, dark mode preference, language selection, onboarding step.

- Form State (React Hook Form): All form data managed by RHF with Zod schemas. Multi-step forms use RHF's context to persist across steps.

- Auth State (NextAuth session): User session, role, permissions. Available via useSession hook or server-side getServerSession.

## 3.4 Internationalization (i18n) Implementation

Multi-language is a first-class feature, not an afterthought. Architecture decisions:

- Routing: Use Next.js middleware-based locale detection with /[locale]/ prefix routing. E.g., /en/ai-tools, /de/ai-tools, /hi/ai-tools. Default locale (en) has no prefix for cleaner URLs.

- Translation Files: Use next-intl or next-i18next. Store translations in /messages/en.json, /messages/de.json, etc. Organize by namespace: common, listings, reviews, news, dashboard, admin.

- Content Translation: Static UI strings are translated manually (hire translators for Tier 1 languages). User-generated content (listings, reviews) stays in original language with an optional "translate" button using an LLM API.

- News Translation: AI-generated news summaries are auto-translated at creation time into all supported languages. Store each translation as a separate row with language field.

- SEO Per Language: Each localized page gets unique meta titles/descriptions, hreflang tags, and its own entry in the sitemap. This is critical for ranking in local search results.

- Initial Languages (8): English, Spanish, German, French, Hindi, Portuguese, Japanese, Korean. Add more based on traffic data.

## 3.5 Technical SEO Implementation in Next.js

- Metadata API: Use Next.js generateMetadata() for dynamic meta tags on every page. Each listing, category, comparison, and news article gets unique title, description, and Open Graph tags.

- Structured Data: Inject JSON-LD schema on every relevant page: Organization (homepage), Product + AggregateRating (listing), Review (review page), Article (news), BreadcrumbList (all pages), FAQPage (pricing/guides), ItemList (category pages).

- Sitemap: Auto-generated XML sitemap via Next.js sitemap.ts that dynamically pulls all listing slugs, category slugs, news articles, and comparison pages from the database. Submit to Google Search Console.

- Robots.txt: Allow all public pages, block dashboard and admin routes, reference sitemap URL.

- Canonical URLs: Set canonical on every page to prevent duplicate content (especially for comparison pages where A-vs-B and B-vs-A exist).

- Performance: Target Core Web Vitals: LCP < 2.5s, FID < 100ms, CLS < 0.1. Use Next.js Image component, font optimization, code splitting, and React Server Components to minimize JS bundle.

- Internal Linking: Every listing page links to its category, alternatives, and related comparisons. Every news article links to relevant listings. Build a dense internal link graph.

# Phase 4: News Engine & AI Pipeline

The Inshorts-style news module is your unique differentiator. This is a separate background service that runs continuously, feeding fresh content into the main application.

## 4.1 News Pipeline Architecture

- Step 1 — Source Ingestion (Every 15 minutes): A scheduled BullMQ job fetches RSS feeds from 100+ tech news sources. Store raw articles in a staging table with: title, full_text, source_url, source_name, published_date, raw_html.

- Step 2 — Deduplication: Hash-based deduplication (title + source similarity) prevents the same story from multiple syndication sources. Use cosine similarity on title embeddings for fuzzy matching.

- Step 3 — Relevance Filtering: Classify articles as relevant/irrelevant using a lightweight classifier. Only process articles about AI, SaaS, startups, tech, and your directory categories. Discard general news, opinion pieces, and clickbait.

- Step 4 — AI Summarization: Send relevant articles to the LLM (GPT-4o-mini or Claude Haiku) with a structured prompt: "Summarize this article in exactly 60-80 words. Include: what happened, who is involved, why it matters. Write in a neutral news tone. Output JSON with: headline (max 10 words), summary, category, tags."

- Step 5 — Category Classification: The LLM also classifies each article into your directory taxonomy. Map to the closest category and add up to 3 tags.

- Step 6 — Translation: For each approved summary, generate translations into all 8 supported languages using the LLM. Store each translation as a separate record.

- Step 7 — Image Selection: Extract the Open Graph image from the source article. If unavailable, use a category-specific default gradient/illustration.

- Step 8 — Editorial Queue: AI-generated summaries go into a moderation queue. Editors can approve, edit, or reject. Target: approve 50–100 articles per day across all categories.

- Step 9 — Publishing: Approved articles are published to the live news feed, indexed in Meilisearch, and added to the sitemap.

## 4.2 RSS Source List (Initial 100+ Sources)

- Tier 1 (daily, high-priority): TechCrunch, VentureBeat, The Verge, Ars Technica, Wired, MIT Technology Review, The Information, Hacker News (top stories RSS)

- AI-Specific: AI News, The Decoder, Hugging Face Blog, OpenAI Blog, Google AI Blog, Anthropic Blog, DeepMind Blog, Papers With Code

- SaaS/Startup: SaaStr Blog, First Round Review, a16z Blog, Y Combinator Blog, Indie Hackers, SaaS Weekly, Baremetrics Blog, ChartMogul Blog

- Funding/Business: Crunchbase News, PitchBook News, CB Insights, Fortune Term Sheet, Bloomberg Technology, Reuters Technology

- Regional Tech: Inc42 (India), Tech.eu (Europe), TechNode (China/Asia), e27 (Southeast Asia), Wamda (MENA), Startup Daily (Australia)

- Product Launches: Product Hunt RSS, BetaList RSS, Launching Next RSS

## 4.3 LLM Prompt Engineering for Summarization

The prompt template for consistent, high-quality summaries:

System Prompt: "You are a tech news editor. Summarize articles in exactly 60-80 words. Be factual, neutral, and concise. Include: what happened, who is involved, and why it matters to the tech/startup community. Never add opinions. Output valid JSON with keys: headline (max 10 words), summary (60-80 words), primary_category (one of: [category list]), tags (array of 1-3 tags), sentiment (positive/neutral/negative), relevance_score (1-10)."

Cost estimate: At 100 articles/day × ~1,500 tokens per (input article + output summary) × 8 languages = ~1.2M tokens/day. Using GPT-4o-mini at $0.15/1M input + $0.60/1M output ≈ $0.50–$1.50/day. Very affordable at scale.

# Phase 5: Backend Development Deep Dive

Backend runs parallel with frontend (W7–W14). Here's the week-by-week breakdown:

| Week | Backend Tasks | Key Technical Decisions |
| --- | --- | --- |
| W7 | Database: Run Prisma migrations for all tables. Seed script: 50 categories, 500 listings, 2000 reviews, 20 users, 100 news articles. API: CRUD for listings and categories. | Use Prisma with connection pooling (PgBouncer). Set up database indexes: slug (unique), category_id, full-text on name+description. |
| W8 | Auth: NextAuth.js v5 setup with Google, GitHub, LinkedIn OAuth + email magic links. Role-based middleware. Session management with JWT + Redis. | Store refresh tokens in Redis. Set up RBAC middleware that checks role on every protected route. |
| W9 | Reviews: Submit, verify, moderate, respond. Review aggregation (calculate average ratings, distribution). Helpful/not helpful voting. | Use database triggers or Prisma middleware to recalculate listing averages on review insert/update. |
| W10 | Search: Meilisearch integration. Index listings and news. Configure faceted filters (category, rating, price, deployment). Typo tolerance and synonym dictionary. | Sync Prisma to Meilisearch via webhook/event system. Custom ranking rules: rating > review_count > recency. |
| W11 | Payments: Stripe integration. Product/Price setup for 4 tiers. Checkout sessions, subscription management, webhook handling (created, updated, cancelled, failed). | Use Stripe Customer Portal for self-service billing. Store subscription status in DB, sync via webhooks. Handle upgrade/downgrade proration. |
| W12 | Analytics: Track page views, clicks, leads per listing. Aggregate daily/weekly/monthly. Build analytics API endpoints. Geographic breakdown via IP geolocation. | Use a lightweight event tracking table. Batch-insert page views. Pre-compute aggregates via cron job to avoid slow queries. |
| W13 | Leads: Lead capture API. Email notifications to company on new lead. Lead status management (new/contacted/converted). Export to CSV. Webhook for CRM integration. | Rate limit lead submissions per IP. Send email via Resend immediately + queue for batch digest. |
| W14 | News Pipeline: Full BullMQ worker setup. RSS fetcher, deduplication, LLM summarization, translation, editorial queue, publishing. Schedule jobs every 15 minutes. | Separate worker process (apps/news-worker). Use Redis-backed BullMQ. Retry failed jobs with exponential backoff. Monitor queue health. |

# Phase 6: Testing & Quality Assurance

Comprehensive testing across 4 layers ensures a reliable launch.

## 6.1 Testing Strategy

| Test Type | Tool | Coverage Target | What to Test |
| --- | --- | --- | --- |
| Unit Tests | Vitest | 80%+ of utility functions, hooks, Zod schemas | Validation schemas, data transformers, helper functions, custom hooks, API route handlers |
| Component Tests | Vitest + React Testing Library | All interactive components | Button states, form validation, search behavior, filter interactions, card rendering with various data |
| Integration Tests | Vitest + MSW (Mock Service Worker) | All API integrations | API calls, error handling, loading states, authentication flows, payment flows |
| E2E Tests | Playwright | 10 critical user journeys | Full registration flow, listing submission, review writing, news browsing, search, comparison, checkout, dashboard |
| Visual Regression | Playwright screenshots or Chromatic | All pages at 3 breakpoints | Catch unintended visual changes on every PR |
| Performance Tests | Lighthouse CI + WebPageTest | All public pages | Core Web Vitals: LCP < 2.5s, FID < 100ms, CLS < 0.1, TTI < 3.8s |
| Accessibility Tests | axe-core + Playwright | All pages WCAG 2.1 AA | Color contrast, keyboard navigation, screen reader labels, focus management, ARIA attributes |
| Security Tests | OWASP ZAP + manual review | All API endpoints | XSS, CSRF, SQL injection, auth bypass, rate limiting, input sanitization |
| Load Tests | k6 or Artillery | API endpoints | Handle 1000 concurrent users, 100 requests/sec on listing pages, search < 200ms at load |

## 6.2 Critical E2E Test Scenarios (Playwright)

- New User Registration: Visit homepage → Click sign up → Enter email → Verify email → Complete profile → Land on user dashboard

- Company Listing Submission: Log in as company → Navigate to submit listing → Complete all 7 wizard steps → Select Growth plan → Complete Stripe checkout → Listing appears in moderation queue

- Review Writing: Log in as user → Find listing → Click write review → Complete rating + text → Submit → Review appears on listing (after moderation)

- Search & Filter: Enter search query → Verify results appear → Apply category filter → Apply rating filter → Results update → Click listing → Arrive at correct page

- News Browsing: Visit news page → See category tabs → Switch category → Scroll/swipe through articles → Click article → See full summary → Click source link → Opens in new tab

- Comparison Flow: View listing A → Click "Compare" → Select listing B → View comparison page → All feature rows populated → Share button works

- Plan Upgrade: Log in as free company → Navigate to billing → Select Growth plan → Enter Stripe test card → Subscription activated → Dofollow link now active on listing

- Admin Moderation: Log in as admin → View pending listings queue → Review listing details → Approve → Listing goes live → Company receives email notification

- Multi-language: Switch language to German → Verify all UI strings translated → Check meta tags in DE → News shows German summaries → URL has /de/ prefix

- Mobile Responsive: Run all above tests at 375px viewport width → Verify hamburger menu, swipe gestures, touch targets, no horizontal scroll

# Phase 7: Deployment & Infrastructure

## 7.1 Infrastructure Architecture

- Frontend (Vercel): Next.js deployed on Vercel. Edge functions for middleware (locale detection, auth checks). Automatic preview deploys for every PR. Custom domain with Cloudflare DNS.

- Database (Neon or Supabase): Managed PostgreSQL with connection pooling, auto-scaling, branching for preview environments. Point-in-time recovery. Daily automated backups.

- Redis (Upstash): Serverless Redis for sessions, rate limiting, caching, and BullMQ job queues. Global replication for low latency.

- Search (Meilisearch Cloud): Managed Meilisearch instance. Auto-sync with database via webhook. Faceted search indexes for listings and news.

- File Storage (Cloudflare R2): S3-compatible object storage for logos, screenshots, media. Served via Cloudflare CDN with image optimization.

- News Worker (Railway or Render): Long-running Node.js process for the news pipeline. Auto-restart on crash. Health check endpoint.

- Email (Resend): Transactional email delivery. React Email templates for consistent branding.

- CDN (Cloudflare): Full-site CDN with edge caching, DDoS protection, Web Application Firewall, bot management.

- Monitoring (Sentry + Better Stack): Error tracking on both frontend and backend. Uptime monitoring with 1-minute checks. Log aggregation. Alerting via Slack/email.

## 7.2 CI/CD Pipeline (GitHub Actions)

Every push to a PR triggers:

- Lint & Type Check: ESLint + TypeScript compiler on all packages (2 minutes)

- Unit & Component Tests: Vitest across all packages (3 minutes)

- Build Check: Next.js build for both web and admin apps (4 minutes)

- E2E Tests: Playwright tests against preview deployment (8 minutes)

- Visual Regression: Screenshot comparison on key pages (5 minutes)

- Security Scan: npm audit + Snyk vulnerability check (2 minutes)

- Preview Deploy: Vercel automatically deploys preview URL for the PR

On merge to main:

- Database Migration: Run Prisma migrations against staging, then production

- Deploy to Staging: Full deployment to staging environment for smoke testing

- Smoke Tests: Automated health checks and critical path tests on staging

- Deploy to Production: Zero-downtime deployment to production via Vercel

- Post-Deploy Checks: Verify all health endpoints, check error rates in Sentry

## 7.3 Environment Strategy

| Environment | Purpose | Database | URL |
| --- | --- | --- | --- |
| Local | Developer machines | Docker PostgreSQL (local) | localhost:3000 |
| Preview | PR review (auto-deployed) | Neon branch (isolated) | pr-123.preview.yourdomain.com |
| Staging | Pre-production testing | Staging DB (copy of prod schema) | staging.yourdomain.com |
| Production | Live site | Production DB | yourdomain.com |

# Phase 8: SEO & Content Seeding (Pre-Launch)

Before opening the platform to the public, seed it with enough content to demonstrate value and begin ranking in search.

## 8.1 Listing Seeding Strategy

- Week 15 — Seed 500 Listings: Manually research and create 500 high-quality listings across your top 20 categories. Source data from company websites, Crunchbase, LinkedIn, and existing directories. Each listing should have: name, description, logo, 2+ screenshots, pricing info, feature list, category, and tags.

- Week 16 — Auto-Populate Data: Build a scraper/enrichment script that pulls public data (logo, description, pricing page, team size, funding) from company websites and Crunchbase. This fills in gaps and ensures listings are comprehensive.

- Week 17 — Outreach for Claims: Email the 500 seeded companies inviting them to claim and enhance their free profiles. Template: "Your company is listed on [Platform Name]. Claim your profile to respond to reviews, add media, and access analytics."

## 8.2 Programmatic SEO Pages

Generate these high-value pages automatically from your database:

- Category Pages (50+): /ai-tools, /saas-platforms, /ai-tools/chatbots, /saas-platforms/crm, etc. Each with unique description, listing grid, and category news feed.

- Comparison Pages (500+): /compare/chatgpt-vs-claude, /compare/hubspot-vs-salesforce. Auto-generate for all listing pairs within the same category. Use LLM to write unique comparison introductions.

- Alternatives Pages (500+): /alternatives/notion, /alternatives/slack. Auto-generate for every listed tool. Include ratings comparison and feature highlights.

- "Best Of" Pages (100+): /best/ai-writing-tools-2026, /best/crm-for-startups. Curated lists by category, updated quarterly.

- City/Country Pages (50+): /startups/india, /saas/germany. For listings with geographic data, create location-specific directory pages.

## 8.3 Schema Markup Checklist

| Page Type | Schema Types | Key Properties |
| --- | --- | --- |
| Homepage | Organization, WebSite, SearchAction | name, url, logo, description, sameAs (social links), potentialAction (search) |
| Category Page | CollectionPage, ItemList | name, description, itemListElement (top listings) |
| Listing Page | SoftwareApplication, Product, AggregateRating, Review | name, description, image, offers (pricing), aggregateRating, review (top 3) |
| Comparison Page | ItemList, Product (x2) | Two products with rating comparison data |
| News Article | NewsArticle, Article | headline, datePublished, author, publisher, image, articleBody |
| Review Page | Review, Rating | author, datePublished, reviewRating, itemReviewed |
| Pricing Page | Product, Offer (x4 tiers) | name, price, priceCurrency, description per tier |
| All Pages | BreadcrumbList | Full breadcrumb path from homepage to current page |

# Phase 9: Launch Strategy & Post-Launch Plan

## 9.1 Pre-Launch Checklist (Week 17)

- All critical pages built and tested at all breakpoints

- 500+ listings seeded with rich data

- 100+ news articles published across categories

- Payment system tested end-to-end with Stripe test mode and live mode

- Email templates tested (welcome, review request, lead notification, payment receipt, password reset)

- SSL certificate configured, all pages served over HTTPS

- robots.txt, sitemap.xml, and Google Search Console set up

- Sentry error tracking active on production

- Uptime monitoring configured with alerting

- GDPR/privacy compliance: cookie banner, privacy policy, data export capability

- Performance audit: all pages score 90+ on Lighthouse

- Accessibility audit: all pages pass WCAG 2.1 AA

- Security audit: OWASP top 10 addressed, rate limiting active, input sanitization verified

- Backup and disaster recovery plan documented and tested

- Load testing: platform handles 1000+ concurrent users without degradation

## 9.2 Launch Week Plan (Week 18)

- Day 1 (Monday): Soft launch. Deploy to production. Invite 50 beta users (friendly founders, team connections). Monitor error rates, performance, and user behavior closely.

- Day 2 (Tuesday): Fix any critical bugs found. Refine onboarding based on beta feedback. Monitor all systems.

- Day 3 (Wednesday): Product Hunt launch. Submit with compelling headline, video demo, and founder story. Coordinate community upvotes. Post to Hacker News "Show HN".

- Day 4 (Thursday): Social media blitz. Share on Twitter/X, LinkedIn, Reddit (r/SaaS, r/startups, r/artificial). Publish launch blog post.

- Day 5 (Friday): Email outreach to the 500 seeded companies with launch announcement. Begin paid claim-your-profile campaign.

- Weekend: Monitor, respond to feedback, fix issues. Prepare week 2 marketing content.

## 9.3 Post-Launch Iteration Cycle (Week 19+)

Establish a continuous improvement rhythm:

- Daily: Monitor error rates, review moderation queue, approve news articles, respond to support tickets.

- Weekly: Review analytics (traffic, signups, conversions, churn). Ship 2–3 improvements or bug fixes. Publish 5–10 news articles per category.

- Bi-Weekly: Sprint planning. Prioritize features based on user feedback and business impact. Demo new features to team.

- Monthly: Publish "Best Of" guides for top categories. Send category newsletter to subscribers. Review SEO performance and adjust.

- Quarterly: Award badges to top-rated listings. Publish industry report. Review pricing and plans. Evaluate new language/market expansion.

# Phase 10: Team Structure & Budget Estimates

## 10.1 Minimum Viable Team

| Role | Count | Responsibility | Monthly Cost (USD, Remote) |
| --- | --- | --- | --- |
| Full-Stack Lead Developer | 1 | Architecture decisions, backend, DevOps, code reviews, technical leadership | $4,000–$8,000 |
| Frontend Developer (React) | 1–2 | All React pages, component library, responsive design, accessibility, performance | $3,000–$6,000 each |
| Backend Developer | 1 | APIs, database, payments, search, background jobs, news pipeline | $3,000–$6,000 |
| UI/UX Designer | 1 (part-time after launch) | Figma designs, user testing, design system maintenance, new feature design | $2,000–$4,000 |
| Content/SEO Manager | 1 | Seed listings, write guides, manage news editorial queue, SEO optimization, outreach | $1,500–$3,000 |
| Founder/Product Manager | 1 (you) | Product strategy, marketing, sales, partnerships, customer support | N/A (equity) |

Total monthly team cost estimate: $13,500–$27,000 depending on location (lower for India/Eastern Europe, higher for US/UK/Germany).

## 10.2 Infrastructure Costs (Monthly)

| Service | Tier | Monthly Cost |
| --- | --- | --- |
| Vercel (Frontend Hosting) | Pro Plan | $20 |
| Neon or Supabase (PostgreSQL) | Pro Plan | $25–$50 |
| Upstash (Redis) | Pay-as-you-go | $10–$30 |
| Meilisearch Cloud | Build Plan | $30–$60 |
| Cloudflare R2 (File Storage) | Pay-per-use | $5–$15 |
| Cloudflare (CDN + DNS) | Pro Plan | $20 |
| Resend (Email) | Pro Plan | $20–$50 |
| OpenAI API (News Summarization) | Pay-per-use | $30–$60 |
| Railway or Render (News Worker) | Starter Plan | $10–$25 |
| Sentry (Error Monitoring) | Team Plan | $26 |
| Better Stack (Uptime + Logs) | Starter Plan | $24 |
| GitHub (Repository) | Team Plan | $4/user |
| Figma (Design) | Professional | $15/editor |
| Domain + SSL | Annual | $15–$30 |
| Total Infrastructure |  | $250–$450/month |

# Phase 11: Complete Tooling & Service Reference

Every tool and service needed for the entire project lifecycle:

| Category | Tool | Purpose | Free Tier? |
| --- | --- | --- | --- |
| Design | Figma | UI/UX design, prototyping, component library, developer handoff | Yes (3 files) |
| Design | Phosphor Icons or Lucide | Consistent icon set across Figma and React | Yes (open source) |
| Design | Coolors / Realtime Colors | Color palette generation and accessibility testing | Yes |
| Code | VS Code + Cursor | Code editor with AI-assisted development | Yes / $20/mo |
| Code | GitHub Copilot | AI pair programming for faster development | $10/mo |
| Code | ESLint + Prettier | Code linting and formatting (automated via CI) | Yes |
| Code | Storybook | Component development and documentation | Yes |
| Framework | Next.js 15 | React framework with SSR/SSG/ISR | Yes |
| Framework | Tailwind CSS 4 | Utility-first CSS framework | Yes |
| Framework | shadcn/ui | Accessible React components built on Radix | Yes |
| Database | Prisma | TypeScript ORM with migrations and type generation | Yes |
| Database | Prisma Studio | Visual database browser for development | Yes |
| Testing | Vitest | Unit and integration testing | Yes |
| Testing | Playwright | End-to-end browser testing | Yes |
| Testing | MSW | API mocking for integration tests | Yes |
| Analytics | PostHog | Product analytics, feature flags, session replays | Yes (1M events) |
| Analytics | Google Search Console | SEO performance monitoring | Yes |
| Analytics | Ahrefs or Semrush | Backlink monitoring, keyword tracking, competitor analysis | $29–$139/mo |
| Marketing | Resend | Transactional and marketing email | Yes (3000/mo) |
| Marketing | Buffer or Typefully | Social media scheduling | Yes (limited) |
| Project Mgmt | Linear or GitHub Projects | Issue tracking, sprint planning, roadmap | Yes (Linear free) |
| Communication | Slack or Discord | Team communication + community | Yes |
| Documentation | Notion or Docusaurus | Internal docs, API docs, knowledge base | Yes |

# Master Execution Checklist

Use this as your weekly tracking checklist. Check off each item as completed.

## Weeks 1–4: Design Phase

- ☐ Figma workspace and file structure created

- ☐ Design tokens (colors, typography, spacing, shadows) defined as Figma Variables

- ☐ Complete atom components built in Figma (buttons, inputs, badges, etc.)

- ☐ Complete molecule components built in Figma (cards, search bar, filters, etc.)

- ☐ Complete organism components built in Figma (navbar, footer, hero, etc.)

- ☐ All 26 public pages designed (desktop + tablet + mobile)

- ☐ All 12 company dashboard pages designed

- ☐ All 10 admin dashboard pages designed

- ☐ All 7 email templates designed

- ☐ Interactive prototypes for 6 critical user flows

- ☐ Design review with stakeholders completed

- ☐ Developer handoff prepared (Figma Dev Mode, annotations, asset exports)

## Weeks 5–6: Project Setup

- ☐ Monorepo initialized with Turborepo + pnpm workspaces

- ☐ Next.js apps scaffolded (web + admin)

- ☐ TypeScript strict mode + ESLint + Prettier configured

- ☐ Tailwind CSS configured with design tokens from Figma

- ☐ shadcn/ui initialized with theme customization

- ☐ Prisma schema defined for all tables

- ☐ Docker Compose for local PostgreSQL + Redis + Meilisearch

- ☐ Database migrations and seed script working

- ☐ NextAuth.js v5 configured with Google + GitHub + LinkedIn + Magic Link

- ☐ Storybook set up for component development

- ☐ Vitest + React Testing Library + Playwright configured

- ☐ GitHub Actions CI pipeline: lint + typecheck + test + build

- ☐ Vercel project connected with preview deploys

- ☐ Environment variables documented and .env.example updated

## Weeks 7–14: Development

- ☐ Shared UI component library complete (atoms, molecules, organisms)

- ☐ All public pages implemented and responsive

- ☐ All company dashboard pages implemented

- ☐ All admin dashboard pages implemented

- ☐ All API endpoints implemented and tested

- ☐ Search integration (Meilisearch) working with faceted filters

- ☐ Payment system (Stripe) fully integrated

- ☐ Review system with verification pipeline working

- ☐ Lead capture system with email notifications working

- ☐ Analytics dashboard showing real data

- ☐ i18n implemented for 8 languages with locale routing

- ☐ News pipeline: RSS ingestion + AI summarization + editorial queue + publishing

- ☐ Structured data (JSON-LD) on all page types

- ☐ Dynamic sitemap generation working

## Weeks 15–17: Testing & Content

- ☐ Unit test coverage > 80% on critical paths

- ☐ 10 E2E test scenarios passing in Playwright

- ☐ Performance audit: all pages Lighthouse 90+

- ☐ Accessibility audit: WCAG 2.1 AA compliance

- ☐ Security audit: OWASP top 10 addressed

- ☐ Load testing: handles 1000+ concurrent users

- ☐ 500+ listings seeded with rich data

- ☐ 100+ news articles published

- ☐ 50+ comparison pages auto-generated

- ☐ 50+ alternatives pages auto-generated

- ☐ Google Search Console configured and sitemap submitted

- ☐ Analytics (PostHog) tracking all key events

## Weeks 18–19: Launch

- ☐ Production deployment successful

- ☐ SSL, CDN, and DNS configured correctly

- ☐ Error monitoring (Sentry) active and alerting

- ☐ Uptime monitoring active

- ☐ Soft launch with beta users completed

- ☐ Critical bugs from beta fixed

- ☐ Product Hunt launch executed

- ☐ Social media launch campaign executed

- ☐ Email outreach to seeded companies sent

- ☐ Post-launch monitoring: error rates, performance, traffic normal

- ☐ Week 2 content and marketing plan ready

This execution plan covers everything from pixel-perfect Figma designs to production deployment. Follow each phase sequentially for the design and setup phases, then run frontend and backend development in parallel from Week 7 onwards. The key to success is maintaining the discipline to complete the Figma design phase thoroughly before writing React code — it will save weeks of rework later.